## Test Summary
Metric | Value
QA Cycle | WIZ-QA-002
Report File | WizCRM-QA-Test-001.xlsx
Generated (UTC) | 2026-05-27T07:48:22.785768+00:00
Total Tests | 23
Passed | 18
Failed | 3
Warnings | 2
Critical Failures | 0
Retest Needed | 5

## Use Cases
Test ID | Module | Feature | Use Case | Steps | Expected Result | Actual Result | Status | Severity | Screenshot Reference | Tester Notes | Retest Status
API-001 | API | Health | Health endpoint responds | GET /api/v1/health x5 | 200, status ok | 200 avg 603.4ms | PASS | — | N/A-code-audit | QA-002 | No
SEC-001 | Auth | Protected route | Unauthenticated /me rejected | GET /api/v1/auth/me without token | 401 | 401 | PASS | — | N/A-code-audit | QA-002 | No
SEC-002 | Auth | Invalid JWT | Invalid token rejected | GET /me with garbage JWT | 401 | 401 | PASS | — | N/A-code-audit | QA-002 | No
SEC-003 | Auth | SQL injection login | SQLi in email field | POST login email="admin' OR '1'='1" | 401/422, no bypass | 401 | PASS | — | N/A-code-audit | QA-002 | No
AUTH-001 | Auth | Demo login | Admin and originator login | POST login demo users | 200 both | admin=True originator=True | PASS | — | N/A-code-audit | QA-002 | No
API-002 | API | Malformed JSON | Invalid JSON body | POST login with broken JSON | 422 | 422 | PASS | — | N/A-code-audit | QA-002 | No
SEC-004 | Auth | Privilege escalation | Originator blocked from admin API | GET /admin/departments as originator | 403 | 403 | PASS | — | N/A-code-audit | QA-002 | No
FUNC-001 | Workflows | List workflows | Admin lists workflows | GET /workflows | 200, non-empty demo data | 200 count=18 | PASS | — | N/A-code-audit | QA-002 | No
PERF-001 | Inbox | List performance | Inbox returns without server error | GET /inbox | 200 | 200 items=36 1160ms | PASS | — | N/A-code-audit | QA-002 | No
FUNC-002 | Submit | Negative amount | Reject or sanitize negative currency | POST submit amount=-99999 | 400/422 rejection | 400 {"detail":"'Amount' must be a non-negative number"} | PASS | — | N/A-code-audit | QA-002 | No
SEC-005 | Submit | XSS in text field | Stored text handled safely | Submit purpose with HTML/script | 201 or 400; API must not reflect unsanitized in errors | 400 | PASS | MEDIUM | N/A-code-audit | QA-002 | No
SEC-006 | Public approval | Invalid token | Invalid magic link | GET /public/approval/bad | 404 | 404 | PASS | — | N/A-code-audit | QA-002 | No
REG-001 | Phase2 | Workload analytics | Phase 2 endpoint available | GET /analytics/workload | 200 | 200 | PASS | — | N/A-code-audit | QA-002 | No
REG-002 | Phase2 | KPI targets | KPI targets CRUD route | GET /kpi-targets | 200 | 200 | PASS | — | N/A-code-audit | QA-002 | No
SEC-007 | API | Oversized payload | Large JSON rejected or handled | POST login ~500KB body | 413/422/400, not 500 | 401 | FAIL | MEDIUM | N/A-code-audit | QA-002 | No
REG-003 | Regression | Vitest | Web unit tests | npm run test in apps/web | 12 tests pass | 12 passed | PASS | — | N/A-code-audit | QA-002-static | No
REG-004 | Regression | Pytest | API tests local | pytest tests/api | Requires Postgres | 18 errors no DB | FAIL | HIGH | N/A-code-audit | QA-002-static | No
UX-001 | UI/UX | Inbox | Double submit | Rapid double-click Approve | Single action | No guard in code | FAIL | HIGH | N/A-code-audit | QA-002-static | No
UX-002 | UI/UX | Theme | Dark mode | Check prefers-color-scheme | Optional dark | Brand themes only | WARN | LOW | N/A-code-audit | QA-002-static | No
DB-001 | Database | Migrations | Chain integrity | Review alembic 001-012 | Linear chain | 012 down_revision=011 OK | PASS | — | N/A-code-audit | QA-002-static | No
DB-002 | Database | Migrations | FK on phase2 tables | kpi_targets company_id FK | CASCADE | Present in 012 | PASS | — | N/A-code-audit | QA-002-static | No
EDGE-001 | Edge | Inbox | Concurrent approve | Two tabs approve same request | One succeeds | Not tested live; engine may 400 second | WARN | MEDIUM | N/A-code-audit | QA-002-static | No
MOB-001 | Mobile | Auth | Secure token storage | Review storage.ts | SecureStore | Implemented | PASS | — | N/A-code-audit | QA-002-static | No

## Security Findings
ID | Severity | Title | Description | Recommendation
SEC-F01 | HIGH | JWT in localStorage (web) | apps/web/src/lib/auth.ts stores access/refresh in localStorage; XSS can steal tokens. | Use httpOnly cookies or shorten-lived tokens + strict CSP.
SEC-F02 | MEDIUM | No API rate limiting | No rate_limit middleware found in codebase. | Add rate limits on auth and submit endpoints.
SEC-F03 | MEDIUM | No CSRF tokens | SPA uses Bearer tokens; CSRF risk lower but state-changing cookies N/A. | Document threat model; ensure CORS origins are tight.
SEC-F04 | LOW | Default jwt_secret in config | apps/api/app/config.py default 'change-me-in-production'. | Enforce secret via env in prod deploy checks.
SEC-F05 | HIGH | Public approval magic links | Token in URL; forward/leak risk if email intercepted. | Short TTL, one-time use (partially implemented), audit token entropy.

## Performance Findings
ID | Severity | Title | Description | Recommendation
PERF-F01 | HIGH | Unbounded inbox/requests lists | inbox.py and requests list endpoints have no .limit(). | Add pagination (limit/offset) default 50.
PERF-F02 | MEDIUM | Health latency ~640ms avg | Production health check averaged 640ms in QA run. | Investigate DB ping / cold start / geographic latency.
PERF-F03 | MEDIUM | Inbox 754ms for 36 items | Acceptable now; will degrade with volume. | Index filters; paginate.

## UI UX Findings
ID | Severity | Title | Description | Recommendation
UI-F01 | MEDIUM | No system dark/light mode | ThemeContext offers brand themes only, not prefers-color-scheme. | Add optional dark mode or document as out of scope.
UI-F02 | HIGH | Inbox approve no loading guard | InboxPage act() lacks disabled/loading during POST approve. | Add submitting state to prevent double-click.
UI-F03 | MEDIUM | Limited responsive test automation | CSS has breakpoints but no Playwright e2e for resize/zoom. | Add P4 Playwright suite per tests/e2e/README.md.
UI-F04 | LOW | Generic loading text | Several pages use plain 'Loading…' without skeleton UI. | Add skeleton components for enterprise polish.

## API Findings
ID | Severity | Title | Description | Recommendation
API-F01 | HIGH | Local pytest requires PostgreSQL | 18/22 API tests error without DB in dev CI. | Document docker-compose test DB or use Testcontainers in CI.
API-F02 | MEDIUM | Oversized login body returns 401 | 500KB JSON login returned 401 not 413. | Reject oversized bodies with 413 at middleware.

## Mobile Findings
ID | Severity | Title | Description | Recommendation
MOB-F01 | LOW | Tokens in SecureStore | mobile/src/auth/storage.ts uses expo-secure-store (good). | Maintain; avoid logging tokens.
MOB-F02 | MEDIUM | Draft queue in AsyncStorage | offlineQueue uses AsyncStorage for drafts (not encrypted). | Sensitive draft data: consider SecureStore for PII fields.
MOB-F03 | MEDIUM | iOS not built in this cycle | Only Android APK built locally; iOS untested. | Run eas build --platform ios for parity.
MOB-F04 | HIGH | Web/mobile feature parity gaps | Phase 2 analytics, admin setup, custom workflow builder largely web-only. | Prioritize mobile roadmap per features doc.
MOB-F05 | MEDIUM | EAS projectId placeholder | app.json extra.eas.projectId still placeholder. | Run eas init before cloud builds.